## Sheet1
RISK | LIKELIHOOD IN ANY ONE MONTH | LIKELIHOOD OVER MESOCOSM TRIAL | MITIGATION AND COUNTERMEASURE OPTIONS | ESTIMATED COST OF MEASURE | DIFFICULTY OF IMPLEMENTATION | LIKELY EFFECTIVENESS OF MEASURE | RELIABILITY OF MEASURE | GO/ NO GO
Habitat effect obscures flake nutriation effects |  | 0.8 | Add a control mesocosm having flakes with the only added mineral being silica
Flake removal by sinking or consumption by pelagic organisms or seabirds |  | 0.7 | Add a control mesocosm having flake numbers that are replenished periodically to make up for losses
Revise flake manufacturing method
Mesocosm contamination by dead organisms or buoyant material |  |  | Prompt removal
Storm, ship, wildlife or other damage to mesocosms or their contents |  | 0.5 | Have mesocosm redundancy at three, widely different locations, including one in a protected, small (preferably coral) island lagoon or shoal
Make some mesocosms semi-submersible so that they can temporarily be buoyed below wave action
Mesocosm rupture |  | 0.3 | Repair and redundancy
Undesirable colonisation of the mesocosms by large marine life forms. |  | 0.4 | Sonic countermeasures
Design mesocosm to have protective spikes, gratings or barriers and minimal places for colonisation or roosting
If thought necessary, instal mesh or transparent covers to each mesocosm
Excessive fouling of mesocosm walls |  | 0.4 | Periodic cleaning, possibly from outside via ultrasonic means
Interference, theft, vandalism, sabotage, loss of mesocosm or part of its equipment |  | 0.3 | Maintain secrecy until mesocosm experiments end
Multiple mesocosm sites
Irregular surveillance by ship visits, aircraft, drones and (preferably hidden) buoy-mounted cameras sending photos by comms to NIO
Notices and a loudspeaker to warn off trespassers
Naval or meteorological surveillance by aerial/satellite photography and ship tracking systems
Arrest and charging by coastguard authorities
Sea rescue |  | 0.1 | Install a radio alert button and instructions on the mesocosm superstructure
Mooring line breakage, possibly due to storm, trawling or a dragging anchor |  | 0.2 | Multiple, spring-loaded mooring lines
Radio beacon(s) on mesocosms. Recovery
Equipment malfunction |  | 0.7 | Good maintenance, backup and redundancy
Power loss |  | 0.3 | Backup systems
Outlier results |  | 0.2 | Multiple mesocosm installations at different locations
Results differ with location and conditions |  | 0.4 | Sensor recordings and analysis